## Boom
|  | Verification Matrix for STEREO/IMPACT/Boom | [15 empty] | Revision Date: 11/14/02
Revision Number: 3
Hardware Description |  | Test
Level of Assembly | Item | Deploy Test, Room Temperature | Deploy test, Thermal Vac | First Motion, Thermal Vac | Stiffness, Proof Load | Vibration, Sinusoidal | Vibration, Random | Shock | Acoustics | Thermal Vacuum | Thermal cycle | Thermal balance | EMC/EMI | Magnetics | Bakeout | Deployment contamination | Contamination Inspection | Comments
C | Proto | X |  |  | X
C | EM | X |  |  | X | X | X | X | [7 empty] | X |  | Qual levels
C | PF/FS | X | X |  | X | X | X | X |  | X | X |  |  | X |  |  |  | Protoflight levels
C | FM1 | X |  | X | X | X | X | H |  | X | X | X | X | X | H |  | X | Acceptanec levels
C | FM2 | X |  | X | X | X | X | H |  | X | X |  |  | X | H |  | X | Acceptance levels
Legend:
| Level of Assembly | Unit Type | [7 empty] | X = | Test required
[10 empty] | A = | Analysis
| C = Component | BB = |  |  | Breadboard |  |  |  |  | H = | Test at higher level of assembly (with instruments)
| I = Instrument | EM = |  |  | Engineering Model
|  | PT = |  |  | Prototype
|  | PF/FS = |  |  | Protoflight / Flight Spare
|  | FM1 = |  |  | Flight unit #1
|  | FM2 = |  |  | Flight unit #2

## MAG
|  | Verification Matrix for STEREO/IMPACT/MAG | [16 empty] | Revision Date: 9/7/01
Revision Number: 1
Hardware Description |  | Test
Level of Assembly | Item | Elect. test, rm. Temp | Bench Calibration | Elect. Test, hot | Elect. Test, cold | Vibration, Sinusoidal | Vibration, Random | Shock | Acoustics | Thermal Vacuum | Voltage margins | Thermal cycle | Thermal balance | >100 hours Operation | EMC/EMI | Magnetics | Bakeout | Contamination | Comments
C | Sensor, EM | X | X
C | Sensor, F | X | X | X | X | H | H | H |  | X |  | X | H | H | H |  | H | X
C | Electronics, EM | X | X | H | H | [8 empty] | H
C | Electronics,F | X | X | X | X | H | H | H |  | H | X | H | H | H | H |  | H | X
Legend:
| Level of Assembly | Unit Type | [7 empty] | X = | Test required
[10 empty] | A = | Analysis
| C = Component | BB = | Breadboard | [6 empty] | H = | Test at higher level of assembly
| I = Instrument | EM = | Engineering Model | [7 empty] | (Boom for sensor, IDPU for electronics)
|  | PT = | Prototype
|  | PF = | Protoflight
|  | F = | Flight

## SWEA
Verification Matrix for STEREO IMPACT SWEA instrument | 2002-11-06
X (CESR)
X (CESR)
X(CESR)
X(CESR)
X(CESR)
X(UCB)
X(UCB)
X(UCB)
X(UCB)
X(UCB)
ETU 1
x (CESR)
x (CESR)
x (CESR)
x (CESR)
x (CESR)
x (CESR)
x (CESR)
x (CESR)
x (CESR)
x (CESR)
X(CESR)
X(CESR)
x (CESR)
x (CESR)
x (CESR)
x (CESR)
x (CESR)
x (CESR)
x (CESR)
X(UCB)
x (CESR)
x (CESR)
x (CESR)
x (UCB)
X(UCB)
X(UCB)
X (CESR)
X (CESR)
X(CESR)
X(CESR)
X(CESR)
X(CESR)
X(CESR)
Gain
Threshold
Dead Time
Current transfert ratio
Electrical tests (gain, threshold)
Electrical tests
Thermal tests & calib.
Bake-out
Vibrations
Electrical tests
Gain and noise tests (in vacuum)
Beam calibration
Interface verification
Thermal balance
Thermal test in vacuum
1/ Component Level
MCP
Preamplifier
Optocouplers
2/ Subsystem Level
Preampli – board
HVPS board
All boards (3)
3/ Instrument
Environmental tests on
complete unit at UCB
SPARE
FM
ETU2
TEST
HARDWARE DESCRIPTION

## STE
|  | Verification Matrix for STEREO/IMPACT/STE | [17 empty] | Revision Date: 11/7/2002
Revision Number: 2
Hardware Description |  | Test
Level of Assembly | Item | Elect. test, rm. Temp | Bench Calibration | Elect. Test, hot | Elect. Test, cold | Vibration, Sinusoidal | Vibration, Random | Self Shock | Acoustics | Thermal Vacuum | Voltage margins | Thermal cycle | Thermal balance | Life Test | EMC/EMI | Magnetics | Beam Calibration | Bakeout | Contamination | Comments
C | Detector, EM | X
C | Detector, F | X | [16 empty] | X
C | Preamp, BB | X | X
I | Instrument, ETU | X | X | X | X |  |  | X | A |  | X | [5 empty] | X
I | Instrument, PF (FM1) | X | X | X | X | H | H | X |  | X | X |  | X | X | H | X | X | X | X
I | Instrument, F (FM2) | X | X | X | X | H | H | X |  | X | X |  |  | X | H | X | X | X | X
Legend:
| Level of Assembly | Unit Type | [7 empty] | X = | Test required
[10 empty] | A = | Analysis
| C = Component | BB = | Breadboard | [6 empty] | H = | Test at higher level of assembly
| I = Instrument | EM = | Engineering Model
|  | PF = | Protoflight
|  | F = | Flight

## SIT
|  |  | Verification Matrix for STEREO/IMPACT/SEP/SIT | [18 empty] | Revision Date: 2002/11/8
Revision Number: 2
Hardware Description |  | Tests
Level of Assembly | Item | Vacuum | Alphas | Elect. test, rm. Temp | Bench Calibration | Elect. Test, hot | Elect. Test, cold | Vibration, Sinusoidal | Vibration, Random | Self Shock | Acoustics | Thermal Vacuum | Voltage margins | Thermal cycle | Thermal balance | Life Test | EMC/EMI | Magnetics | Beam Calibration | Bakeout | Contamination | Comments
C | Detectors, F |  | X | [8 empty] | X
C | Foils PT | [9 empty] | X
C | Telescope PF,F | X | X | [17 empty] | X
C | Energy board, EM |  |  | X |  | X | X | [5 empty] | X
C | Energy board, F |  |  | X | [16 empty] | X
C | TOF Board, EM |  |  | X |  | X | X | [5 empty] | X
C | TOF Board, F |  |  | X | [16 empty] | X
C | HVPS EM |  |  | X |  | X | X | [5 empty] | X
C | HVPS F |  |  | X | [16 empty] | X
I | Instrument W/O Telescope | [18 empty] | X
I | Instrument, PF | X | X | X | X | X | X | X | X | X |  | X | X | X | X | X | H | X | X | X | X | Protoflight levels
I | Instrument, F | X | X | X | X | X | X | X | X | X |  | X | X | X |  | X | H | X | X | X | X | Acceptance levels
Legend:
| Level of Assembly | Unit Type | [9 empty] | X = | Test required
[12 empty] | A = | Analysis
| C = Component | BB = | Breadboard | [8 empty] | H = at a higher level
| I = Instrument | EM = | Engineering Model
|  | PT = | Prototype
|  | PF = | Protoflight
|  | F = | Flight

## SEPT
|  |  |  | Verification Matrix for STEREO/IMPACT/SEPT | [16 empty] | Revision Number 2
Revision Date 2002-11-7
Hardware Description |  |  |  | Tests
Level of Assembly | Item | Spacecraft | Quantity | Thermal Analysis | Struct. Analysis | Modal Survey/ Sine Sweep | Random Vibration | Self Shock | Acoustics | Mass Properties | Pressure Profile | Mechanical Function | Life Test | EMC/EMI | Magnetics | Leak | Thermal | Thermal Balance | Thermal Vacuum | Bakeout | Comments
I | SEPT-E (T) |  | 1 | A | A | [6 empty] | X | X |  | X |  | X |  |  |  | Engineering Model
I | SEPT-E (PF) | A | 1 |  |  | X | X | X | X | X |  | X | X | H | X |  |  | X | X | X | Test to qualification level
I | SEPT-E (F2) | B | 1 |  |  | X | X | X |  | X |  | X | X | H | X |  |  | X | X | X | Test to acceptance level
I | SEPT-NS (F1) | A | 1 |  |  | X | X | X |  | X |  | X | X | H | X |  |  | X | X | X | Test to acceptance level
I | SEPT-NS (F2) | B | 1 |  |  | X | X | X |  | X |  | X | X | H | X |  |  | X | X | X | Test to acceptance level
Legend:
A=Analysis
X=Test
H=Test at a higher level

## HET
|  |  |  | Verification Matrix for STEREO/IMPACT/SEP/HET | [18 empty] | Revision Date: 11/12/02
Revision Number: 3
Hardware Description |  |  |  | Tests
Level of Assembly | Item | Noise & Brkdown | Thermal vacuum | Alphas &/or Accelerator | Elect. test, rm. Temp | Elect. Test, hot | Elect. Test, cold | Vibration, Sinusoidal | Vibration, Random | Shock | Acoustics | Pressure change | Voltage margins | Thermal cycle | Thermal balance | Life Test | EMC/EMI | Magnetics | Radiation | Leak | Bakeout | Contamination | Comments
C | Detectors, PT | X | X | X | X | X | X |  | X |  | X |  |  | X | [7 empty] | X | Vibration at manufacturer
C | Detectors, F | X | X | X | X | X | X |  | X |  |  |  |  | X | [8 empty] | Vibration at manufacturer
C | Hybrids, PT |  |  |  | X | X | X | [11 empty] | X
C | Hybrids, F |  |  |  | X | X | X | [8 empty] | X |  |  |  | X |  | X | Also standard class H tests
C | HET board, EM |  |  |  | X | X | X | [5 empty] | X
C | HET board, F |  |  |  | X | X | X | [5 empty] | X | [7 empty] | X | X
C | Connectors F | [20 empty] | X
I | Instrument F1 |  | H | X | X | X | X | H | H | A |  | A | X |  | X | X | H | H |  |  | X | X | Protoflight levels
I | Instrument, F2 |  | H | X | X | X | X | H | H | A |  | A | X |  |  | X | H | H |  |  | X | X | Acceptance Levels
Legend:
| Level of Assembly | Unit Type | [9 empty] | X = | Test required
[12 empty] | A = | Analysis
| C = Component | BB = |  | Breadboard | [7 empty] | H = test at a higher level of assembly
| I = Instrument | EM = |  | Engineering Model
|  | PT = |  | Prototype
|  | F = |  | Flight
|  | F1 = |  | Flight unit #1
|  | F2 = |  | Flight unit #2

## LET
|  |  |  | Verification Matrix for STEREO/IMPACT/SEP/LET | [18 empty] | Revision Date: 11/08/02
Revision Number: 5
Hardware Description |  | Tests
Level of Assembly | Item | Noise & Brkdown | Thermal vacuum | Alphas &/or particle accelerator | Elect. test, rm. Temp | Elect. Test, hot | Elect. Test, cold | Vibration, Sinusoidal | Vibration, Random | Shock | Acoustics | Pressure change | Voltage margins | Thermal cycle | Thermal balance | Life Test | EMC/EMI | Magnetics | Radiation | Leak | Bakeout | Contamination | Comments
C | Detectors, PT | X | X | X | X | X | X |  | X |  | X |  |  | X | [7 empty] | X | Acoustics in BB with windows
C | Detectors, F | X | X | X | X | X | X |  | X |  |  |  |  | X
C | Hybrids, PT |  |  |  | X | X | X | [11 empty] | X
C | Hybrids, F |  |  |  | X | X | X | [8 empty] | X |  |  |  | X |  | X | Also standard class H tests
C | LET detector/MISC board, EM |  |  |  | X | X | X | [5 empty] | X
C | LET detector/MISC board, F |  |  |  | X | [15 empty] | X | X
C | Connectors, F | [20 empty] | X
C | Windows, BB | [7 empty] | X |  | X |  |  | X | [8 empty] | Include L1 detectors for vib & acoustics
I | Instrument, F1 |  | H | X | X | X | X | H | H | A | X | A | X |  | X | X | H | H |  |  | X | X | Protoflight levels for vib; full EMC at suite
I | Instrument, F2 |  | H | X | X | X | X | H | H | A | X | A | X |  |  | X | H | H |  |  | X | X | Acceptance levels for vib; workmanship for EMC
Legend:
| Level of Assembly | Unit Type | [9 empty] | X = | Test required
[12 empty] | A = | Analysis
| C = Component | BB = |  | Breadboard | [7 empty] | H = | test at a higher level of assembly
| I = Instrument | EM = |  | Engineering Model
|  | PT = |  | Prototype
|  | F = |  | Flight
|  | F1 = |  | Flight unit #1
|  | F2 = |  | Flight unit #2

## SEPCentral
|  |  |  | Verification Matrix for STEREO/IMPACT/SEP/SEP Central | [17 empty] | Revision Date: 11/08/02
Revision Number: 3
Hardware Description |  |  |  | Tests
Level of Assembly | Item | Noise & Brkdown | Thermal vacuum | Alphas | Elect. test, rm. Temp | Elect. Test, hot | Elect. Test, cold | Vibration, Sinusoidal | Vibration, Random | Shock | Acoustics | Pressure change | Voltage margins | Thermal cycle | Thermal balance | Life Test | EMC/EMI | Magnetics | Leak | Bakeout | Contamination | Comments
C | LVPS, EM |  |  |  | X | X | X | [5 empty] | X |  |  |  | X
C | LVPS, F |  |  |  | X | [11 empty] | X |  |  |  | X
C | Analog Post-reg, EM |  |  |  | X | X | X | [5 empty] | X
C | Analog Post-reg, F |  |  |  | X | [14 empty] | X | X
C | Detector bias supply, EM |  |  |  | X | X | X | [5 empty] | X
C | Detector bias supply, F |  |  |  | X | [14 empty] | X | X
C | Logic board, EM |  |  |  | X | X | X | [5 empty] | X
C | Logic board, F |  |  |  | X | [14 empty] | X | X
C | Connectors, F | [14 empty] | X |  |  |  |  | X
C | Harnesses, F | [19 empty] | X
I | Instrument, EM |  |  |  | X | X | X | [5 empty] | X | [8 empty] | Electrical EM only
I | Instrument, F1 |  | H |  | X | X | X | H | H | A |  | A | X |  | X | X | H | H |  | X | X | Protoflight levels for vib; full EMC at suite
I | Instrument, F2 |  | H |  | X | X | X | H | H | A |  | A | X |  |  | X | H | H |  | X | X | Acceptance levels for vib; workmanship EMC
Legend:
| Level of Assembly | Unit Type | [9 empty] | X = | Test required
[12 empty] | A = | Analysis
| C = Component | BB = |  | Breadboard | [7 empty] | H = | test at a higher level of assembly
| I = Instrument | EM = |  | Engineering Model
|  | PT = |  | Prototype
|  | PF = |  | Protoflight
|  | F = |  | Flight
|  | F1 = |  | Flight unit #1
|  | F2 = |  | Flight unit #2

## IDPU
|  | Verification Matrix for STEREO/IMPACT/IDPU | [16 empty] | Revision Date: 11/06/02
Revision Number: 2
Hardware Description |  | Test
Level of Assembly | Item | Elect. test, rm. Temp | Elect. Test, hot | Elect. Test, cold | Vibration, Sinusoidal | Vibration, Random | Shock | Acoustics | Pressure change | Voltage margins | Thermal Vacuum | Thermal balance | >100 hours Operation | EMC/EMI | Magnetics | Leak | Bakeout | Contamination | Comments
C | PWB, EM | X | [7 empty] | X
I | IDPU EM | X | X | X | [5 empty] | X |  |  | X | X |  |  |  |  | EMC CE test on EM
C | PWB, F | X | [7 empty] | X | [6 empty] | X
I | IDPU, F | X | X | X | X | X |  |  | A | X | X |  | X | H | X |  | X | X | EMC at Suite level
Legend:
| Level of Assembly | Unit Type | [9 empty] | X = | Test required
[12 empty] | A = | Analysis
| C = Component | BB = |  | Breadboard | [7 empty] | H = at higher level of assembly
| I = Instrument | EM = |  | Engineering Model
|  | PT = |  | Prototype
|  | PF = |  | Protoflight
|  | F = |  | Flight