## BOOM Variance
UID | BOOM Element | IRT Finish | Current Finish | Delta (Work Days) | Current Total Slack | Cause & Corrective Action
513 | Deliver SWEA/STE-D FM 1 (stays at UCB for Boom Suite FM 1 I&T) | 2004-08-17 | 2004-09-03 | 13d | -42 d
483 | Deliver SWEA/STE FM 1 LVPS (stays at UCB) | 2004-07-06 | 2004-07-28 | 16d | -42 d
176 | Boom Suite FM 1 Ready for Delivery to APL | 2004-10-25 | 2004-11-09 | 11d | -23 d
489 | Deliver SWEA/STE FM 2 LVPS (stays at UCB) | 2004-08-17 | 2004-08-24 | 5d | -22 d
514 | Deliver SWEA/STE-D FM 2 (stays at UCB for Boom Suite FM 2 I&T) | 2004-10-28 | 2004-11-04 | 5d | -5 d
504 | Deliver STE-D FM 2 (stays at UCB for SWEA/STE-D FM 2 I&T) | 2004-08-06 | 2004-08-13 | 5d | 12 d
509 | Deliver Boom Structure FM 2 (stays at UCB for Boom Suite FM 2 I&T) | 2004-09-09 | 2004-09-16 | 5d | 12 d
1120 | FM 2 Boom/MAG/STE-U I&T | 2004-08-09 | 2004-08-16 | 5d | 12 d
502 | Deliver STE-U FM 2 (stays at UCB for BOOM Suite FM 2 I&T) | 2004-08-06 | 2004-08-13 | 5d | 12 d
284 | IDPU S/W Build #3 (also goes to UNH) | 2004-07-21 | 2004-08-11 | 15d | 29 d

## SEP Variance
UID | SEP Element | IRT Finish | Current Finish | Delta (Work Days) | Current Total Slack | Cause & Corrective Action
1044 | Deliver SIT FM 1 to CIT for SEP I&T and Suite EMC | 2004-08-18 | 2004-09-17 | 21d | -40 d
1049 | Deliver SIT FM 1 back to GSFC for Environmental Testing (after EMC Test) | 2004-09-22 | 2004-10-12 | 13d | -37 d
1048 | Final Delivery of SIT FM 1 to APL | 2004-11-15 | 2004-12-01 | 11d | -37 d
909 | SIT FM 2 Start I&T | 2004-07-29 | 2004-09-02 | 25d | -36 d
1393 | FM 2 EMI/EMC Test at CalTech | 2004-10-14 | 2004-12-16 | 43d | -36 d
179 | SEP Suite FM 2 Ready for Delivery to APL | 2004-12-10 | 2004-12-20 | 6d | -36 d
917 | SIT FM 2 @ GSFC for Environmental Testing | 2004-10-19 | 2004-11-01 | 9d | -36 d
491 | Deliver SIT FM 2 HVPS (to UMD) | 2004-07-08 | 2004-08-18 | 49d | -36 d
636 | HET Electronics Board Complete | 2004-07-29 | 2004-08-05 | 5d | 14 d