## BOOM Variance
UID | BOOM Element | Baseline Finish | Current Finish | Delta (Work Days) | Current Total Slack | Cause & Corrective Action
513 | Deliver SWEA/STE-D FM 1 (stays at UCB for Boom Suite FM 1 I&T) | 2004-06-11 | 2004-07-12 | -21 | 2 d | Radiation Source on STE Door delayed STEA Schedule by 2 weeksDelays due to fixes in Power Supply Design. Changes implemented. Power Supply instrument delay
176 | Boom Suite FM 1 Ready for Delivery to APL | 2004-08-13 | 2004-09-21 | -26 | 11 d | IDPU Power Supply is pushing this task out.
177 | Boom Suite FM 2 Ready for Delivery to APL | 2004-09-28 | 2004-10-06 | -6 | 14 d | Power Supply Issues
514 | Deliver SWEA/STE-D FM 2 (stays at UCB for Boom Suite FM 2 I&T) | 2004-08-27 | 2004-09-07 | -6 | 14 d
1052 | Boom Suite FM 2 EMC | 2004-09-14 | 2004-09-22 | -6 | 14 d
481 | Deliver IDPU FM 1 LVPS (stays at UCB) | 2004-04-23 | 2004-05-25 | -22 | 15 d | Board layout problems and recent fixes to the Power Supply Design. New boards in fabrication.
493 | IDPU FM 1 Complete (to UCB for Boom I&T, then to CIT for SEP I&T, Suite EMC, BO & Final Boom I&T) | 2004-05-21 | 2004-06-23 | -22 | 15 d
294 | IDPU FM 1 I & T | 2004-04-30 | 2004-06-02 | -22 | 15 d
504 | Deliver STE-D FM 2 (stays at UCB for SWEA/STE-D FM 2 I&T) | 2004-05-10 | 2004-06-29 | -35 | 18 d
503 | Deliver STE-D FM 1 (stays at UCB for SWEA/STE-D FM 1 I&T) | 2004-04-14 | 2004-05-05 | -15 | 19 d
508 | Deliver Boom Structure FM 1 (stays at UCB for Boom Suite FM 1 I&T) | 2004-05-27 | 2004-06-16 | -13 | 20 d
501 | Deliver STE-U FM 1 (stays at UCB for BOOM Suite FM 1 I&T) | 2004-04-20 | 2004-05-07 | -13 | 20 d
1119 | FM 1 Boom/MAG/STE-U I&T | 2004-04-26 | 2004-05-13 | -13 | 20 d
331 | Integrate FM 1 Boom Structure subassemblies & Harness Completion | 2004-04-05 | 2004-04-16 | -9 | 25 d
332 | FM 1 Boom Structure Deployment Test | 2004-04-19 | 2004-04-30 | -9 | 25 d
498 | Deliver MAG FM 1 (to UCB for IDPU/BOOM Suite FM 1 I&T) | 2004-03-29 | 2004-04-29 | -23 | 26 d
489 | Deliver SWEA/STE FM 2 LVPS (stays at UCB) | 2004-04-26 | 2004-05-28 | -24 | 29 d
509 | Deliver Boom Structure FM 2 (stays at UCB for Boom Suite FM 2 I&T) | 2004-06-18 | 2004-08-05 | -34 | 36 d
502 | Deliver STE-U FM 2 (stays at UCB for BOOM Suite FM 2 I&T) | 2004-05-10 | 2004-06-29 | -35 | 36 d
1120 | FM 2 Boom/MAG/STE-U I&T | 2004-05-14 | 2004-07-05 | -35 | 36 d
487 | Deliver IDPU FM 2 LVPS (stays at UCB) | 2004-04-30 | 2004-07-07 | -47 | 37 d
494 | IDPU FM 2 Complete (to CIT for SEP I&T, then to UCB for Boom I&T, Boom EMC, BO & Final Boom I&T) | 2004-05-28 | 2004-08-04 | -47 | 37 d
517 | Deliver STE-U FM 1 Interface (stays at UCB for IDPU FM 1 I&T) | 2004-02-27 | 2004-04-16 | -35 | 42 d
499 | Deliver MAG FM 2 (to UCB for IDPU/BOOM Suite FM 2 I&T) | 2004-03-29 | 2004-05-10 | -30 | 71 d
284 | IDPU S/W Build #3 (also goes to UNH) | 2004-04-13 | 2004-05-13 | -22 | 85 d
518 | Deliver STE-U FM 2 Interface (stays at UCB for IDPU FM 2 I&T) | 2004-03-01 | 2004-04-23 | -39 | 89 d

## SEP Variance
UID | SEP Element | Baseline Finish | Current Finish | Delta (Work Days) | Current Total Slack | Cause & Corrective Action
520 | IMPACT Suite FM 1 EMC Testing at UCB | 2004-07-12 | 2004-08-17 | -26 | -8 d | Date of test is being reworked given the dates of Instument Delivery
1044 | Deliver SIT FM 1 to CIT for SEP I&T and Suite EMC | 2004-06-21 | 2004-07-27 | -26 | -8 d | Limited Manpower. Added test Engineer in early March
946 | SEP FM 1 Suite I&T Complete | 2004-06-28 | 2004-08-03 | -26 | -8 d | Being driven out by SIT development. Note:UID 1044
178 | SEP Suite FM 1 Ready for Delivery to APL | 2004-09-14 | 2004-10-12 | -19 | -3 d
1020 | Deliver HET FM 1 w/o replacement detectors (to CIT for SEP Suite I&T) | 2004-06-02 | 2004-07-01 | -21 | -3 d | Board assembly issues. Boards currently in test.
1049 | Deliver SIT FM 1 back to GSFC for Environmental Testing (after EMC Test) | 2004-07-14 | 2004-08-19 | -26 | -3 d | Replan of activities of STE-D. Adequate slack.
1048 | Final Delivery of SIT FM 1 to APL | 2004-09-01 | 2004-10-12 | -27 | -3 d
1035 | Deliver LET FM 1 (stays at CIT for SEP I&T) | 2004-06-08 | 2004-06-29 | -15 | -1 d
734 | Integrate LET FM 1 Housing With Detectors | 2004-06-08 | 2004-06-29 | -15 | -1 d
1043 | Deliver SIT FM 2 to CIT for SEP I&T | 2004-07-26 | 2004-08-16 | -15 | 1 d
909 | Integrate SIT FM 2 HVPS and SIT FM 2 Telescope Without Electronics | 2004-05-21 | 2004-06-14 | -15 | 1 d
995 | FM 2 EMI/EMC Test at CalTech | 2004-08-18 | 2004-08-30 | -8 | 1 d
179 | SEP Suite FM 2 Ready for Delivery to APL | 2004-10-12 | 2004-10-25 | -9 | 2 d
491 | Deliver SIT FM 2 HVPS (to UMD) | 2004-04-13 | 2004-05-24 | -29 | 2 d
1201 | Inspection and Final Assembly of HET Telescope | 2004-04-30 | 2004-05-24 | -16 | 2 d
1202 | Deliver HET Telescope (stays at GSFC) | 2004-04-30 | 2004-05-24 | -16 | 2 d
1046 | Deliver SIT FM 2 back to GSFC for Environmental Testing | 2004-08-20 | 2004-09-01 | -8 | 2 d
1047 | Final Delivery of SIT FM 2 to APL | 2004-10-12 | 2004-10-25 | -9 | 2 d
1031 | Deliver all SEP Cen FM 1 Boards to SEP I&T (stays at CIT) | 2004-05-10 | 2004-06-01 | -15 | 13 d
482 | Deliver SEP FM 1 LVPS (to Caltech) | 2004-04-06 | 2004-05-03 | -19 | 16 d
1192 | Deliver SEP Enclosure to CIT | 2004-03-30 | 2004-05-21 | -38 | 19 d
964 | SEP Suite I&T FM 2 Complete | 2004-08-11 | 2004-08-23 | -8 | 26 d
1019 | Deliver HET FM 2 w/o replacement detectors (to CIT for SEP Suite I&T) | 2004-06-23 | 2004-07-08 | -11 | 34 d
488 | Deliver SEP FM 2 LVPS (to Caltech) | 2004-04-19 | 2004-06-25 | -48 | 37 d
1028 | Deliver all SEP Cen FM 2 Boards & FM 2 LVPS to SEP I&T (stays at CIT) | 2004-05-10 | 2004-06-25 | -33 | 37 d
1034 | Deliver LET FM 2 (stays at CIT for SEP I&T) | 2004-06-08 | 2004-06-29 | -15 | 41 d
736 | Integrate LET FM 2 Housing With Detectors | 2004-06-08 | 2004-06-29 | -15 | 41 d
636 | HET Electronics Board Complete | 2004-05-13 | 2004-05-21 | -6 | 45 d | During removal of a temporary commercial ACTEL (U200) several pads(29) were lifted. We will build a new board, and repair the other board. One will become a Flight Spare. Continue with testing and switch out boards later on.